

Offshore Petroleum Exploration Guideline: Work-bid

In relation to the *Offshore Petroleum and Greenhouse Gas Storage Act 2006*

**Effective 1 July 2019**

This document has been developed as a general guide only. It is subject to, and does not replace or amend the requirements of the[*Offshore Petroleum and Greenhouse Gas Storage Act 2006*](https://www.legislation.gov.au/Series/C2006A00014)and associated Regulations, which should be read in conjunction with this guideline.

This guideline is made available by the Australian Government for information only. Before relying on this material, users should carefully evaluate the accuracy, currency, completeness and relevance of the information and obtain independent, legal or other professional advice relevant to their particular circumstances.

This document has been prepared by the [Department of Industry, Science, Energy and Resources](https://www.industry.gov.au/) . It will be reviewed and updated as required.

This document is available online at [www.nopta.gov.au](http://www.nopta.gov.au/).

**Contents**

[1. Obtaining a petroleum exploration permit 3](#_Toc2244416)

[How to apply 3](#_Toc2244417)

[Technical evaluation 3](#_Toc2244418)

[Exploration strategy 4](#_Toc2244419)

[Work program 4](#_Toc2244420)

[Technical qualifications 6](#_Toc2244421)

[Financial capacity 7](#_Toc2244422)

[Past Performance 8](#_Toc2244423)

[Bid assessment 8](#_Toc2244424)

[Further information 9](#_Toc2244425)

[Refusal to grant an exploration permit 9](#_Toc2244426)

[2. Petroleum exploration permit conditions and administration 10](#_Toc2244428)

[Overview 10](#_Toc2244429)

[Work program credit 11](#_Toc2244430)

[Suspension or a suspension and extension 11](#_Toc2244431)

[Technical grounds 12](#_Toc2244432)

[Variations 13](#_Toc2244433)

[Exemptions 14](#_Toc2244434)

[Surrenders 14](#_Toc2244435)

[Expiry 15](#_Toc2244436)

[Cancellation 15](#_Toc2244437)

[3. Renewal 16](#_Toc2244438)

[Overview 16](#_Toc2244439)

[How to apply 16](#_Toc2244440)

[Work program 17](#_Toc2244441)

[Refusal to renew an exploration permit 19](#_Toc2244442)

[4. Good Standing Agreement 20](#_Toc2244443)

[Overview 20](#_Toc2244444)

[Options for satisfying a Good Standing Agreement 21](#_Toc2244445)

[Application process 21](#_Toc2244446)

[Criteria and eligibility 22](#_Toc2244447)

[Multiple titleholders 22](#_Toc2244448)

[Monetary value and non-acceptable deductions 22](#_Toc2244449)

[Minimum terms of a Good Standing Agreement 23](#_Toc2244450)

[Satisfaction of a Good Standing Agreement 23](#_Toc2244451)

[Extensions 24](#_Toc2244452)

[Variation to Terms and Conditions 24](#_Toc2244453)

[APPENDICES 25](#_Toc2244454)

[Good Standing Agreement – Flow Chart 25](#_Toc2244455)

# Obtaining a petroleum exploration permit

[Part 2.2, Division 2 of the Offshore Petroleum and Greenhouse Gas Storage Act 2006 (OPGGS Act)](https://www.legislation.gov.au/Series/C2006A00014)

## Overview

1. The Joint Authority awards exploration permits to the applicant who proposes an exploration strategy and work program that will significantly advance the assessment and understanding of the petroleum potential of the area and who has a satisfactory record of past performance. The applicant, in accordance with [section 104(3) of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014), must also demonstrate its technical and financial capacity to deliver the proposed work program.
2. The Joint Authority recognises the essential role of wells in the discovery of petroleum. However, depending on the nature of the area, an exploration well in the primary term may not place an applicant above another applicant who proposes a work program that is logical, coherent and supportable and is considered to be commensurate with the perceived prospectivity of the area.
3. The Joint Authority acknowledges the challenges of exploring in lightly-explored areas. This guideline clarifies the Joint Authority’s expectation of bidding for these areas, specifically around the role of exploration wells.
4. The Joint Authority awards exploration permits subject to a set of standard conditions. If deemed appropriate, the Joint Authority may also place additional conditions on the permit - [section 99 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014).
5. The Commonwealth will respect the confidentiality of any information provided on a ‘Commercial-in-Confidence’ basis.

## How to apply

* 1. Applications must be compliant with the [OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014), the requirements published in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0) notice (gazette notice) inviting applications and also meet the minimum expectations of the Joint Authority, as outlined in this guideline.
  2. Applicants are expected to take into account all relevant matters, such as environmental protection, defence, navigation, native title interests, fisheries and access restrictions applying in areas.
  3. An application form is available online at [NOPTA’s website](http://www.nopta.gov.au/forms/forms.html). For submission details, please refer to the gazette notice.
  4. Applicants may submit any other relevant information they wish to have considered.
  5. Once an application is submitted, the composition and timing of the proposed work program may not be amended through the submission of further information and other changes will not be accepted.
  6. An application must be accompanied by the relevant fee prescribed in schedule 6 of the Offshore Petroleum and Greenhouse Gas Storage (Resource Management and Administration) Regulations 2011 ([RMA Regulations](https://www.legislation.gov.au/Series/F2011L00647)). Detailed information of payment options is provided on [NOPTA's website](http://nopta.gov.au/cost-recovery-and-fees.html#crf_payments).

## Technical evaluation

* 1. The technical evaluation should summarise the applicant’s understanding of the geology and petroleum potential of the release area. It should include the concepts underlying the proposed work program, with sufficient detail to support that program. A sound technical evaluation should include an assessment of relevant data and support the amount of seismic surveying and the number and conceptual targets of wells to be drilled, if applicable.
  2. The technical evaluation should include, but is not limited to, a description of:
     1. The applicant’s assessment of the release area, including potential petroleum systems, and plays within the release area.
     2. Any prospects and leads mapped within the release area, including supporting material such as images, interpreted seismic sections and horizon maps.
     3. The data and/or studies the technical evaluation is based on.
     4. Any geotechnical studies, seismic interpretation, mapping or any other work that has been undertaken as part of the technical evaluation.
     5. How the applicant proposes to utilise any existing data over the release area, including how this data is to be utilised in the proposed work program.

## Exploration strategy

* 1. The exploration strategy should link the technical evaluation with the proposed work program.
  2. Applicants should propose an exploration strategy that has the potential to significantly advance the assessment and understanding of the petroleum potential of the release area. The exploration strategy should support the applicant’s technical evaluation of the release area and the proposed work program for the six-year permit term.
  3. The exploration strategy should explain how the release area will be explored over the permit term, including how the different work program elements will investigate the plays, prospects and leads identified in the technical evaluation of the area.

## Work program

* 1. Proposed work program activities must be stated precisely to avoid ambiguity.
  2. Work programs are divided into a ‘primary’ and ‘secondary’ term.
  3. The first three years of a work program are referred to as the **primary term.** The first three years of the permit term are combined and the minimum work requirements must commence and be completed within that primary term.
  4. Once awarded, the work program commitments for the primary term become guaranteed and cannot be reduced. Work activities that cannot be guaranteed should not be included in the primary term.
  5. Permit Years 4, 5, and 6 are referred to as the **secondary term**. Each year’s work program becomes guaranteed upon entry and the minimum work requirements must commence and be completed within the permit year.

An example of a six-year work program:

| Year | Start date | End date | Activity | Indicative cost $A |
| --- | --- | --- | --- | --- |
| 1-3 | 01/01/2015 | 31/12/2017 | 2,000 km² of 3D seismic reprocessing  2,000 km² of new 3D seismic acquisition and processing  Geophysical and geological studies including seismic interpretation | X00,000  XX,000,000  X00,000 |
| 4 | 01/01/2018 | 31/12/2018 | Geophysical and geological studies including prospect and lead maturation studies | X00,000 |
| 5 | 01/01/2019 | 31/12/2019 | One exploration well | XX,000,000 |
| 6 | 01/01/2020 | 31/12/2020 | Geotechnical and geological studies | X,000,000 |

* 1. The proposed work program for the six-year term must be consistent with the exploration strategy and underpinned by the technical evaluation of the area.
  2. The proposed work program must be regarded as significantly advancing the exploration effort.
  3. The early elements of the proposed work program should be sufficient to enable the later elements to proceed and be aligned with the exploration strategy. This includes the need for the number and timing of wells to be justifiable and be supported by the number and maturity of plays, prospects and/or leads identified i.e. the work program should be pursuable on a dry hole basis.
  4. Proposed work program activities should only include work that will be undertaken within the permit area. Any work, studies or reprocessing proposed outside the permit area, must be clearly differentiated.
  5. Work intended to appraise a known petroleum accumulation in an area may form part of the proposed work program. However, appraisal activities must be clearly differentiated from exploration activities.
  6. Work associated with a known petroleum accumulation will only be considered as exploration work if the applicant provides a sufficient rationale to support an assessment that the activity includes a significant exploration component. This rationale should be consistent with the overall exploration strategy and underpinned by the technical evaluation of the area.
  7. The minimum acceptable work program for an area will vary depending on the size of the area, its perceived prospectivity and its location. At a minimum, it is expected that the proposed work program will contain:
     1. *New operational activities,* such as data acquisition and/or exploration well/s. For areas that are lightly-explored or frontier in nature, operational activities may be other activities, not necessarily exploration wells.
     2. *Reprocessing and/or geophysical and geological studies* to enable a play, lead or prospect to be identified and progressed toward maturing a drillable target.
  8. Where an area is fully covered by 3D seismic data, reprocessing a majority of this data may form part of the proposed work program and can be undertaken instead of acquiring new seismic data. The reprocessing would normally be expected to be from raw data or the quality controlled traces and to utilise techniques not previously undertaken on seismic data within the permit area.
  9. It is expected that at least one exploration well will be proposed during the initial six-year permit term for well-explored areas with good data coverage.
  10. The description of the proposed work program should include:

1. Indicative expenditure in Australian dollars for each activity at current market value.
   * + 1. Operational activities: calculations detailing how the cost of the activities has been estimated should be provided.
2. The number of line kilometres of 2D and proposed line spacing and/or square kilometres of 3D seismic data that will be acquired and processed within the permit area, including:
   * + 1. Full fold numbers within the permit area.
       2. A map showing the indicative location of the 2D lines or 3D survey outline. All existing seismic surveys should be identified on this map.
       3. If known, the parameters and methodology of the seismic acquisition and processing that will be undertaken.
3. The amount, type and details of the applicable dataset of any new reprocessing the applicant proposes to undertake, including:
   * + 1. The number of line kilometres of 2D and/or square kilometres of 3D seismic data that will be reprocessed within the permit area clearly stated.
       2. A map showing the indicative location of the 2D lines or 3D survey outline. All existing seismic surveys should be identified on this map.
       3. If known, the parameters and methodology of the reprocessing that will be undertaken.
4. The number of exploration wells proposed, including indicative plays and target play levels.
5. The nature, scope and objectives of all proposed studies.
6. The licensing or use of any existing exclusive or non-exclusive datasets and, if applicable, how these are proposed to be used in conjunction with any reprocessing or geophysical studies proposed in the work program.
7. Descriptions and the conceptual locations/targets/purpose of other operational activity or surveying proposed.

## Important notes on treatment of new vs existing seismic data

* 1. The reprocessing and interpretation of existing data undertaken during the applicant’s pre-bid evaluation will be taken into account in assessing the relative merits of the proposed work program.
  2. An applicant who pre-licences multi-client data or undertakes reprocessing of pre-licenced multi-client data as part of its pre-bid evaluation and who therefore does not propose the work as part of its work program, will not be disadvantaged. As such, applicants should provide details of pre-bid evaluation work, including the extent of the work undertaken, the outcomes and how this has informed the exploration strategy and proposed work program.

### Non-exclusive seismic data: Multi-client surveys and reprocessing products

* 1. If an applicant proposes to licence non-exclusive seismic data, new or reprocessed, as part of a work program, it should:

1. state whether the data is part of:

* An existing non-exclusive seismic survey or reprocessed data volume, or
* A planned or not-yet-completed non-exclusive seismic survey or reprocessed data project.

1. state when the initial final processed or reprocessed data will become available for licencing
2. ensure that:

* the data is in an industry standard format that is fit for purpose in meeting the objective of the work program,
* the applicant would be able to provide information to NOPTA that demonstrates the work program obligation has been met, and
* the data submission and release requirements can be met.
  1. If the final processed dataset will not become available until after the closing date of bids, this will be assessed as new seismic acquisition for the purposes of the bid assessment.

## Technical qualifications

* 1. An applicant must satisfy the Joint Authority of its technical capacity and competence to undertake the proposed work program. This will include, but not be limited to, the technical capacity and experience of key personnel and/or sub-contractors, and particulars of other current and previous involvement in petroleum exploration.
  2. An applicant should provide details of:
     1. The technical qualifications of the applicant and those of its key employees.
     2. The technical advice that is or will be available to the applicant by way of consultants or other providers.

## Financial capacity

* 1. An applicant must satisfy the Joint Authority that it and/or its consolidated parent entity group has the financial capacity to:
     1. continue as a going concern,
     2. meet its existing (other) title-related commitments including work programs, development and decommissioning obligations, and
     3. undertake the proposed work program.
  2. The assessment of financial capacity will test the applicant(s) ability to meet the commitments associated with the proposed work program in addition to its existing Commonwealth offshore title-related commitments.
  3. When assessing an applicant(s) financial capacity, consideration will be given to the current and future funds available to the applicant and the magnitude and timing of obligations associated with the application, and all other Australian offshore petroleum titles it holds.

Information required to support financial assessment

* 1. To undertake an assessment of the financial capacity of an applicant, details of the current financial resources available and the future financial commitments of the applicant should be provided as follows:
     1. The most recent audited consolidated financial statements including:
        1. Balance Sheet (dated not more than twelve months from the date the application is submitted)
        2. Income Statement
        3. Cash Flow Statement
        4. Notes to the accounts in sufficient detail and in a format consistent with generally accepted accounting principles, and
        5. Prior year comparable financial statements

OR

* + 1. If audited consolidated financial statements are not available, unaudited consolidated financial statements (as per i to v above) can be provided. These must be accompanied by a declaration by the directors stating that the financial statements have been prepared in accordance with International Financial Reporting Standards and that the applicant can continue as a going concern as at the balance sheet date.

Note: if an applicant relies on a parent entity’s accounts to demonstrate financial capacity details of funding methods and any guarantees between the entities should also be provided. The assessment that would have applied to the applicant will apply to the parent entity to determine financial capability.

* 1. Evidence of financial capacity may include:

1. Bank deposits held.
2. Loan facilities – e.g. loan agreements signed by all parties or loan agreements conditional on the award of a title are acceptable, not letters of intent from a loan institution.
3. Other guarantees – e.g. a bank guarantee, or certified statement of an individual’s capacity to fund (high net worth individuals) from an accountant.
4. Forecast cash flows – if an applicant has existing assets and those assets have proven reserves and are in production or production is imminent. (Speculative cash flows, if the assets are not in production and production is not imminent are not acceptable).
5. Track record of successful funding of exploration projects.
6. Proven ability to attract farm in partners.
7. Proven ability to raise capital by public or private means.
8. Letter of guarantee from capital raising entity (although arrangements with financial institutions or brokerage firms that undertake to raise equity on a best effort basis are not adequate evidence of funding).
9. Evidence that a satisfactory Joint Venture Operating Agreement has been or can be reached.

## Past performance

* 1. Past performance of the applicant, parent company or subsidiary company where applicable, and its directors is a factor the Joint Authority will consider during the decision making process unless the company and directors have a current Good Standing Agreement – refer to section 4 of this guideline.
  2. Past performance refers to compliance matters under the OPGGS Act over the previous five years, such as cancellations or expiries in default.
  3. Past performance may also refer to any health, safety and/or environmental incidents within Australia or internationally. The applicant may choose to detail proposed mitigation in relation to these matters within their bid documents. Entering into a Good Standing Agreement does not offset a health, safety and/or environmental past performance record.
  4. The Joint Authority may not offer an exploration permit to an applicant if the applicant’s past performance indicates a history of non-compliance with permit conditions or if the applicant does not demonstrate a proven ability to significantly advance the assessment and understanding of the petroleum potential of permit areas.
  5. The Joint Authority may also consider past performance when ranking multiple applicants in accordance with [section 106(3) of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014), to determine a most deserving applicant.

## Bid assessment

* 1. Bids are assessed by NOPTA and advice is provided to the relevant Joint Authority.
  2. In deciding whether to exercise its discretion to make an offer, the Joint Authority may take into consideration a broad range of factors. These factors may include which bid is likely to progress the most comprehensive understanding of the petroleum prospectivity of the area.
  3. Where there are multiple applicants for the grant of an exploration permit, in determining the applicant who is most deserving, the Joint Authority must have regard to the criteria in section 1.47 of this guideline, in relation to the proposed primary work program.
  4. Where there is a single applicant, the Joint Authority may also have regard to the criteria on section 1.47 of this guideline.
  5. These criteria are, in no particular order:
     1. The relevance of the proposed work program to the technical evaluation and exploration strategy.
     2. The amount, type and timing of seismic acquisition and processing to be carried out, including parameters and methodology.
     3. The amount, type and timing of other surveying and data acquisition to be carried out.
     4. The amount, type and timing of seismic data to be purchased or licenced.
     5. The amount, type and timing of seismic data reprocessing to be carried out, including parameters and methodology.
     6. The type, scope and objectives of the geophysical and geological studies, proposed within the area and how these studies align with other work program activities and the exploration strategy.
     7. The number and timing of exploration wells proposed and their alignment with the perceived prospectivity of the area, supporting program of geological and geophysical work and the number of proposed plays and/or mapped prospects/leads identified.
     8. The past performance of the applicant.
     9. Significant appraisal work over previous petroleum discoveries within the area, if any.
  6. The Joint Authority must be satisfied the applicant has the technical and financial capacity to undertake the proposed work program.
  7. If an applicant cannot be chosen on the basis of the primary work program, using the criteria above, the secondary work program will be assessed and ranked.
  8. After assessing the secondary work programs, if two or more applicants are still considered to be equally deserving of the grant of an exploration permit, in accordance with [section 106(6) of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014) the Joint Authority may invite the applicants to make a written proposal for additional work and expenditure.
  9. If an applicant is made an offer for the grant of an exploration permit and declines the offer, the Joint Authority may make an offer to the second ranked applicant, where applicable.
  10. There is no penalty or disadvantage should an applicant not accept an offer by the Joint Authority.

## Further information

[Section 258 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. The Titles Administrator may clarify any aspect of the bid through a written request for further information.
  2. If further information is requested and not submitted within the specified time, the Joint Authority may by written notice given to the applicant, refuse to consider or take any further action in relation to the application.

## Refusal to grant an exploration permit

* 1. The grounds the Joint Authority may take into account for refusing to grant an exploration permit, include, but are not limited to, circumstances where the:
     1. Proposed work program is assessed to be inferior to that of a competing bid.
     2. Proposed work program is assessed to be inadequate to significantly advance the exploration status of the area.
     3. Proposed work program does not support the technical evaluation.
     4. Joint Authority is not satisfied the applicant possesses the financial capacity to facilitate the proposed work program, in addition to other guaranteed work program commitments in other titles under the OPGGS Act the applicant and/or parent company has an interest in.
     5. Joint Authority is not satisfied the applicant possesses the technical capacity to facilitate the proposed work program.
     6. Joint Authority is not satisfied the past performance of the applicant in Australia or internationally.

# Petroleum exploration permit conditions and administration

## Overview

1. Titleholders are expected to ensure that all obligations under the OPGGS Act, [*Offshore Petroleum and Greenhouse Gas (Regulatory Levies) Act 2003*](https://www.legislation.gov.au/Series/C2004A01202) (OPGGS Levies),the associated regulations, any directions and title conditions are met at all times.
2. Titleholders must comply with the data management and reporting requirements of the [Offshore Petroleum and Greenhouse Gas Storage (Resource Management and Administration) Regulations 2011](https://www.legislation.gov.au/Series/F2011L00647) (RMA regulations).
3. The OPGGS Act allows for a variation, suspension and/or exemption from compliance with work program condition(s). Where warranted, the Joint Authority may also grant an extension to the permit term where a condition has been suspended.
4. The Joint Authority acknowledges elements of an exploration work program or its timing may need to change as:
   * 1. Geological or technical knowledge is gained, requiring additional work i.e. technical grounds; or
     2. If the timing of an activity is impacted by *force majeure* circumstances.
5. All applications are considered by the Joint Authority on a permit-by-permit basis. Therefore, a separate application must be lodged for each permit. Application forms are available on [NOPTA's website](http://www.nopta.gov.au/forms/forms.html).
6. Applications made under [section 264 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014) may be submitted at any time but should not be made later than 60 days before the end of the primary term or the permit year. It is the responsibility of the titleholder to ensure there is sufficient time for a decision to be made before entering the next permit year.
7. There is a fee for applications made under [sections 264 and 269 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014). The fee is prescribed in schedule 6 of the RMA Regulations. Detailed information on payment options is provided on NOPTA’s website.
8. Titles that have a ‘prior usage right’ for the purposes of section 359 of [the *Environment Protection and Biodiversity Protection Act 1999*](https://www.legislation.gov.au/Series/C2004A00485)(EPBC Act) will require consent from the Minister for the Environment before an extension to the permit term can be granted by the Joint Authority – refer to the ‘Offshore Petroleum Guideline: Prior Usage Rights’ on [NOPTA’s website](http://www.nopta.gov.au/forms/forms.html).

## Important notes on work program commitment – seismic data and reprocessing

* 1. A titleholder may meet a seismic surveying commitment by licencing an equivalent amount of non-exclusive seismic data, if the final processed data becomes available after the date the permit was granted.
  2. A titleholder may purchase and/or licence reprocessed seismic data to meet a seismic reprocessing work program commitment subject to the following conditions:
     1. The reprocessed data will only be accepted to the extent it meets, in part or in full, the original work program commitment.
     2. The data must have been reprocessed after the date the permit was granted.
     3. The reprocessing will be from raw data or the quality controlled traces.
     4. The reprocessing must utilise techniques not previously undertaken on seismic data acquired within the permit.
  3. If an applicant proposes to licence data to use in its current form, or to reprocess as part of a work program commitment, it must ensure that:
     1. The data is in an industry standard form that is for purpose in meeting the objectives of the work program.
     2. It is able to provide information to NOPTA that demonstrates the work program commitment has been met.
     3. The data submission and release requirements can be met.

## Work program credit

* 1. The Joint Authority places a standard condition on title instruments that enables the Titles Administrator, at its discretion and by written instrument, to credit activities undertaken within an earlier permit year as meeting the work program commitments of a later permit year.
  2. It is the responsibility of titleholders to obtain the Titles Administrator’s agreement to credit an activity to a later permit year.

## Suspension or a suspension and extension

[Section 264 and 265 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. Titleholders may apply to suspend any of the conditions to which the permit is subject ***or*** apply to suspend any of the conditions to which the permit is subject together with an extension of the permit term – a ‘suspension and extension’.
  2. The Joint Authority considers the work program as a whole when reviewing a suspension or suspension and extension application.
  3. The Joint Authority will generally only consider a suspension with an extension of the permit term if the proposed work program for the subsequent year/s is reliant on the work to be undertaken in the suspended year i.e. the subsequent year consists of an exploration well or other operational activities.
  4. If a suspension application is lodged in the final year of the permit term, the permit will remain in force until a decision is made by the Joint Authority. If the Joint Authority refuses the application, the permit will continue in force for at least two months, effective from the date the titleholder was notified of the refusal. This will ensure the titleholder has time to apply for a renewal of the permit or for the grant of a successor title prior to the expiry of the permit ([section 265A of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)).
  5. A suspension or a suspension and extension will not change the reporting date for the Annual Titles Assessment Report – refer [3.03 of the RMA regulations](https://www.legislation.gov.au/Series/F2011L00647).
  6. A suspension of a permit year suspends the deadline to complete a work program commitment activity or activities. A suspension only will defer the end date of the current permit year but will not alter the end date of subsequent permit years (e.g. in the example below Permit Years 4 and 5 will now run concurrently.)

An example of a 12-month suspension of Permit Year 4:

| Year | Start date | End date | Activity | Indicative cost $A |
| --- | --- | --- | --- | --- |
| 4 | 10/01/2015 | ~~09/01/2016~~  09/01/2017 | 2,000km² 3D seismic acquisition and processing  Geophysical and geological studies  Including interpretation | X,000,000  X00,000 |
| 5 | 10/01/2016 | 09/01/2017 | Geophysical and geological studies including prospect maturation studies | X00,000 |
| 6 | 10/01/2017 | 09/01/2018 | One exploration well | XX,000,000 |

* 1. A suspension and extension will defer the end date of the current permit year and all subsequent permit years.

An example of a 12-month suspension of Permit Year 4 and extension of the permit term:

| Year | Start date | End date | Activity | Indicative cost $A |
| --- | --- | --- | --- | --- |
| 4 | 10/01/2015 | ~~09/01/2016~~  09/01/2017 | 2,000km² 3D seismic acquisition and processing  Geophysical and geological studies including interpretation | X,000,000  X00,000 |
| 5 | ~~10/01/2016~~  10/01/2017 | ~~09/01/2017~~  09/01/2018 | Geophysical and geological studies including prospect maturation studies | X00,000 |
| 6 | ~~10/01/2017~~  10/01/2018 | ~~09/01/2018~~  09/01/2019 | One exploration well | XX,000,000 |

#### Force majeure circumstances

* 1. If the ability of a titleholder to meet a work program commitment is adversely impacted by an event that cannot be reasonably anticipated or controlled during the course of the exploration work program via experience or care (*force majeure*) the Joint Authority may approve a suspension or a suspension and extension.
  2. An application for a suspension or suspension and extension on *force majeure* grounds must include substantial and compelling documentary evidence to demonstrate how the *force majeure* circumstance has adversely impacted the ability to complete the work program, and a Gantt chart showing the proposed schedule for the forward work program.
  3. Commercial circumstances and common risks in the industry are **not considered** to constitute *force majeure*. These may influence the perceived commercial viability of an activity but would not normally prevent an explorer from adhering to its commitment. Such circumstances and risks may include, but are not limited to:
     + avoidable delays in receiving processed/reprocessed data from contractors
     + failure to mature a drillable prospect
     + changes in oil price
     + difficulty attracting a farm-in partner
     + avoidable delays in contracting a drilling rig/seismic vessel
     + difficulty in raising capital
     + disappointing exploration results
     + the need to wait for the results of exploration work undertaken outside the permit area
     + rescheduling of appraisal/development wells ahead of exploration wells.

## Technical grounds

* 1. If the ability of a titleholder to meet an existing work program commitment is affected by new geological knowledge or unexpected technical challenges, the Joint Authority may approve a suspension or a suspension and extension on technical grounds.

Note: if a titleholder proposes additional work activities to address new geological knowledge or unexpected technical challenges, the Joint Authority would generally expect this work to be varied into the work program through an above-commitment work variation (see section 2.24-2.27).

* 1. An application for a suspension and extension on technical grounds must include compelling documentary evidence to demonstrate how these technical grounds have adversely impacted the ability to complete the work program, and a Gantt chart showing the proposed schedule for the forward work program.

## Variations

[Section 264 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. Titleholders may apply to vary any of the conditions to which the permit is subject. In submitting variation applications titleholders should note that:
     + Proposed work program activities to be varied into the permit should only include work that will be undertaken within the permit area. Any work, studies or reprocessing proposed outside the permit area must be clearly differentiated.
     + If a titleholder lodges an application in the last 60 days of the primary term or the relevant permit year, the titleholder may wish to consider lodging a suspension and extension application in the event an adverse decision is made by the Joint Authority.
     + If a titleholder applies for a suspension and variation at the same time, this can be lodged as a single application on the appropriate application form.
  2. A titleholder may apply for:
     + *A work equivalent variation* to replace a guaranteed work activity with an equivalent work activity.
     + *An* a*bove-commitment work variation* to undertake above-commitment work that has critical implications for the assessment of the petroleum potential of the permit area.
     + *A secondary work program variation* to vary the work program conditions in Permit Years 4, 5 and 6 of an initial permit term or Permit Years 4 and 5 of a renewal term.
  3. If the Joint Authority agrees to vary an exploration well out of the permit term, an exploration well is expected to be included in the primary term of the renewal program, should the titleholder elect to renew the permit.

#### Work equivalent variation

* 1. A titleholder may apply to replace a guaranteed work program activity with an equivalent work program activity.
  2. The Joint Authority will generally only agree to a variation if the proposed replacement work program activity is a similar or superior technique and the activity meets or exceeds the objective of the original work program commitment.
  3. It is the responsibility of the titleholder to ensure the Joint Authority has agreed to the work equivalent variation before commencement of the work.

#### Above-commitment work variation

* 1. If a titleholder proposes to undertake significant above-commitment work that will have critical implications for the exploration of the permit area, the Joint Authority may agree to an above-commitment variation, to vary the work into the current permit year so that the work becomes guaranteed.
  2. An application should be supported by technical evidence as to why the work program should be varied, a detailed outline of the proposed new activities, a Gantt chart showing the proposed schedule for the forward work program, and documentary evidence (such as contracts with a relevant service provider to undertake the new activities) in support of the application.
  3. When considering an application for an above-commitment work variation, the Joint Authority may also agree to either a suspension or suspension and extension to enable the titleholder sufficient time to undertake the work.
     + An application for a suspension or suspension and extension should be lodged with the variation application.
  4. Generally in the case of an above-commitment work variation, the Joint Authority will consider up to a 12-month suspension or a 12-month suspension and extension, if supported by the circumstances of the application. However, a longer time frame may be requested and the Joint Authority will consider this on a case-by-case basis and on its merits for circumstances such as when:
     1. A titleholder has entered a permit year with a drilling commitment and is unable to mature a drillable prospect.
     2. The proposed work is significant and assessed to have critical implications on the titleholder’s forward work plans.

#### Secondary work program variation

* 1. A titleholder may apply to vary:
* Individual permit years before entry into the relevant permit year.
* Permit Years 5 *and*6 before entry into Permit Year 5.
* The *whole* secondary work program before entry into Permit Year 4.
  1. An application should be supported by exploration results from the primary term or previous permit years and technical evidence as to why the work program should be varied.

## Exemptions

[Section 264 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. A titleholder may apply to be exempt from compliance with a work program condition. An exemption application may be made on exceptional technical or *force majeure* grounds.
  2. In deciding whether to exempt a titleholder from compliance with a work program condition, the Joint Authority will consider:

1. if the titleholder has demonstrated a significant effort to identify and assess the petroleum potential of the permit and has provided substantial and compelling documentary evidence, and
2. if the objective of the original work program commitment has been met.
   1. The Joint Authority will not exempt a titleholder from an activity if the following permit years are reliant on that work being undertaken.

## Surrenders

[Part 2.12 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. A titleholder may apply for consent to surrender some or all of the blocks that the permit is in force over. An application form is available on NOPTA’s website which provides details of the information that should be provided with the application.
  2. In deciding whether to consent to the surrender, the Joint Authority will consider the provisions of [section 270 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014), including:

1. The status of the work program – ordinarily consent will be refused before the completion of the guaranteed primary term work program commitments.
2. Whether the titleholder has completed all guaranteed work program commitments up to and including the permit year in which the application has been made.
3. Whether there are sufficient grounds in the Joint Authority’s view to warrant the giving of consent to surrender despite non-compliance with any of the criteria outlined in subsection 270(3). In determining if sufficient grounds exist for a surrender in non-compliance (subsection 270(5)), the Joint Authority may consider:
   * + 1. if the titleholder has demonstrated a significant effort to identify and assess the petroleum potential of the permit and has provided substantial and compelling documentary evidence,
       2. if the objective of the original work program commitment has been met, and
       3. other matters as considered relevant by the Joint Authority.
   1. In undertaking its assessment, in accordance with the OPGGS Act, NOPTA consults with the [National Offshore Petroleum Safety and Environmental Management Authority](http://www.nopsema.gov.au/).
   2. Titleholders are expected to ensure any outstanding reports and data are lodged with the surrender application in accordance with the [RMA regulations](https://www.legislation.gov.au/Series/F2011L00647).
   3. If the Joint Authority gives consent to the surrender of the permit, the titleholder may, by written notice given to NOPTA, surrender the whole or part of the permit.
   4. The surrender takes effect the day a notice is published in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0).

## Expiry

* 1. An expiry takes effect on the day the permit ceases to be in force.
  2. Titleholders are not required to lodge an application if it is intended to let a permit expire. However, titleholders may choose to notify NOPTA of this intention before the expiration date.
  3. Prior to the permit expiry, the titleholder should aim to be in a position to maintain their standing with Joint Authority by ensuring that:

1. All conditions of the title, including any work program commitments have been met.
2. All relevant provisions of chapters 2, 4, 6 and part 7.1 of the OPGGS Act and the regulations have been complied with including the submission of all reports and data due and completion of any decommissioning obligations.
3. Any direction(s) given by the responsible Commonwealth Minister, NOPSEMA or the Joint Authority have been complied with.
4. All applicable fees, royalties and the annual titles administration levy have been paid, or appropriate arrangements have been made with NOPTA.
   1. Where a permit expires in default of the permit conditions, the titleholders may apply for a Good Standing Agreement – refer to section 4 of this guideline.
   2. If the permit expires in default of the permit conditions and a Good Standing Agreement is not entered into, the titleholders will be recorded as having a past performance issue that will be used in the decision making process, for a period of five years, effective from the day the expiry is gazetted.
   3. After the expiry of the permit, NOPTA will:
      1. Undertake a compliance check of the title. If any of the matters outlined in section 2.41 are outstanding NOPTA will contact the titleholder.
      2. Issue a formal notice of expiry (or expiry in default) in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0) ([section 708 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)).
      3. Make an entry on the Register of Titles regarding expiry of the title ([section 471 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)).
      4. Advise the titleholders in writing that the title has expired.

## Cancellation

[Part 2.13 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

* 1. Titleholders are expected to ensure all obligations under the OPGGS Act, OPGGS Levies Act, the associated regulations, any directions and permit conditions are met at all times. Failure to comply with any of these obligations, including work program commitments, is a ground for cancellation of the permit.
  2. If there is/are a ground/s for cancellation, before making a decision the Joint Authority will issue the titleholders a written notice of intention to cancel the permit, setting out the reason/s for the proposed cancellation and inviting a written submission to the Joint Authority. Titleholders will be given at least 30 days to submit matters they wish to have considered by the Joint Authority in reaching its final decision.
  3. At the time of receiving a notice of intention to cancel, or earlier, titleholders may choose to submit an application to enter into a Good Standing Agreement – refer to section 4 of this guideline.
  4. Before deciding to cancel a title, the Joint Authority must consider:
     1. any submissions made by the titleholder or other relevant persons, and
     2. take into account any action taken by the titleholder to remove the ground(s) for cancellation, or prevent its recurrence.
  5. The titleholder(s) will be notified in writing if the Joint Authority cancels the title. A cancellation takes effect the day a notice is published in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0).

# Renewal

[Part 2.2, Division 5 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014)

### Overview

1. A titleholder may apply to renew a work program exploration permit. Titleholders should refer to [sections 122 and 123 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014) to determine the number of times a permit may be renewed and the maximum number of blocks that may be applied for.
2. An application must be made at least 90 days before the expiry of the permit. NOPTA may accept applications later than 90 days, but no later than the expiry date. A form for requesting an extension of time to lodge an application for renewal is available on NOPTA’s website.
3. It is the Joint Authority’s expectation that the proposed work program will be supported by an exploration strategy that will significantly advance the assessment and understanding of the petroleum potential of the permit area during the five-year renewal term.
4. The Commonwealth will respect the confidentiality of any information provided on a ‘Commercial-in-Confidence’ basis.
5. Titles that have a ‘prior usage right’ for the purposes of section 359 of the *Environment Protection and Biodiversity Protection Act 1999* (EPBC Act) will require consent from the Minister for the Environment before a renewal can be granted by the Joint Authority – refer to the ‘Offshore Petroleum Guideline: Prior Usage Rights’ on [NOPTA’s website](http://www.nopta.gov.au/forms/forms.html).

## How to apply

* 1. An application form is available on [NOPTA’s website](http://www.nopta.gov.au/forms/forms.html). Refer to the application form for submission details.
  2. An application must be accompanied by the relevant fee prescribed in schedule 6 of the [RMA Regulations](https://www.legislation.gov.au/Series/F2011L00647). Detailed information on payment options is provided on [NOPTA’s website](http://www.nopta.gov.au/cost-recovery-and-fees.html).
  3. A renewal application may be submitted by a titleholder in relation to the blocks specified in the application and should include:
     1. a technical evaluation of the petroleum potential of the area
     2. a work program and activities for the primary term
     3. a work program and activities for the secondary term
     4. an overview of compliance with the permit conditions, chapters 2, 4, 6 and part 7.1 of the OPGGS Act and the associated regulations.
  4. Applications are assessed by NOPTA and advice is provided to the relevant Joint Authority.
  5. NOPTA may clarify any aspect of the renewal application through a written request for further information to the applicant.

## Work program

* 1. The proposed work program for the five-year renewal term must be consistent with the exploration strategy and underpinned by the technical evaluation of the area incorporating results and findings of the previous permit term.
  2. The early elements of the proposed work program should be sufficient to enable the later elements to proceed and be aligned with the exploration strategy. This includes the need for the number of wells to be justifiable and be supported by the number and maturity of plays, prospects and/or leads identified i.e. the work program should be pursuable on a dry hole basis.
  3. Work intended to appraise a known petroleum accumulation in an area may form part of the proposed work program. However, appraisal activities must be clearly differentiated from exploration activities.
  4. Work associated with a known petroleum accumulation will only be considered as exploration work if the titleholder provides a sufficient rationale to support an assessment that the activity includes a significant exploration component. This rationale should be consistent with the overall exploration strategy and underpinned by the technical evaluation of the area.
  5. The first three years of a work program are referred to as the **primary term.** The first three years of the permit term are combined and the minimum work program commitments must commence and be completed within the primary term.
  6. Once the permit is renewed, the primary term work program becomes guaranteed and cannot be reduced. Work program activities that cannot be guaranteed should not be included in the primary term.
  7. Permit Years 4 and 5 are referred to as the **secondary term**. Each year’s work program commitment becomes guaranteed upon entry and the minimum work requirements must commence and be completed within the permit year.

An example of a five-year work program:

| Year | Start date | End date | Activity | Indicative cost $A |
| --- | --- | --- | --- | --- |
| 1-3 | 01/01/2015 | 31/12/2017 | 2,000 km² of 3D seismic reprocessing  Geophysical and geological studies including interpretation, well planning  One exploration well | X00,000  XX,000,000  X00,000 |
| 4 | 01/01/2018 | 31/12/2018 | 1,000 km² of new 3D seismic acquisition and processing | X00,000 |
| 5 | 01/01/2019 | 31/12/2019 | Geophysical and geological studies including post well evaluation and seismic data interpretation | XX,000,000 |

* 1. At a minimum, it is expected the proposed work program will contain:
     1. *New operational activities*, such as data acquisition and/or exploration well/s, in the primary work program.
     2. *Reprocessing and/or geophysical and geological studies* to enable a play, lead or prospect to be identified and progressed toward maturing a drillable target.
  2. Where an area is fully covered by 3D seismic data, reprocessing a majority of this data may form part of the proposed work program and can be undertaken instead of acquiring new seismic data. The reprocessing would normally be expected to be from raw data or the quality controlled traces and to utilise techniques not previously undertaken on seismic data within the permit area.
  3. It is expected that at least one exploration well will be proposed during the five-year permit renewal term. If a well is not proposed, technical justification should be provided in the application addressing why exploration drilling in the renewal term would not be feasible.
     1. If no exploration drilling was undertaken in the previous permit term, it is generally expected an exploration well will be proposed in the renewal as a work program commitment in the primary term.
  4. Work program activities should only include work that is to be undertaken within the permit area. Any work, studies or reprocessing to be undertaken outside the permit area must be clearly differentiated.
  5. The description of the proposed work program for the renewal term should include:

1. Indicative expenditure in Australian dollars for each activity at current market value.
   * + - Operational activities: calculations detailing how the cost of the activities has been estimated should be provided.
2. The number of line kilometres of 2D and proposed line spacing and/or square kilometres of 3D seismic data that will be acquired and processed within the permit area, including:
   * + - Full fold numbers within the permit area.
       - A map showing the indicative location of the 2D lines or 3D survey outline, including any known leads and/or prospects. All existing seismic surveys should be identified on this map.
       - If known, the parameters and methodology of the seismic acquisition and processing that will be undertaken.
3. The amount, type and details of the applicable dataset of any new reprocessing the applicant proposes to undertake, including:
   * + - The number of line kilometres of 2D and/or square kilometres of 3D seismic data that will be reprocessed within the permit area clearly stated.
       - A map showing the indicative location of the 2D lines or 3D survey outline, including any known leads and/or prospects. All existing seismic surveys should be identified on this map.
       - If known, the parameters and methodology of the seismic acquisition and processing that will be undertaken.
4. Descriptions of the prospects and leads mapped within the permit area.
   * Images, seismic sections and horizon maps should be included.
5. The number of exploration wells to be drilled including indicative plays and target play levels.
6. The nature, scope and objectives of any studies.
7. The licensing or use of any existing exclusive or non-exclusive datasets and, if applicable, how these are proposed to be used in conjunction with any reprocessing or geophysical studies proposed in the work program.
8. Descriptions and the conceptual locations targets and purpose of other operational activity or surveying proposed.

## Refusal to renew an exploration permit

* 1. The OPGGS Act provides that the Joint Authority must refuse to renew a permit if there has been non-compliance with permit conditions, the provisions of chapters 2, 4 and 6 and part 7.1 of the OPGGS Act and/or the provisions of the regulations and if the Joint Authority is not satisfied that sufficient grounds exist to warrant the renewal.
  2. Where the Joint Authority intends to refuse to renew an exploration permit, consultation procedures apply under [section 262 of the OPGGS Act](https://www.legislation.gov.au/Series/C2006A00014).

# Good Standing Agreement

## Overview

A. If a titleholder defaults on a guaranteed work program commitment, a Good Standing Agreement (GSA) is a policy mechanism available for the titleholder and their directors, to maintain ‘good standing’ with the Joint Authority.

B. The standing of a company and its directors is a status assigned by the Joint Authority. To be in ‘good standing’ means that over the previous five years the company and/or its directors has not defaulted on:

* + - * Any guaranteed work program commitments, or where a default has occurred, has entered into a Good Standing Agreement.
      * A Good Standing Arrangement/Agreement.

C. By entering into a GSA, the Joint Authority will not consider any default on guaranteed work program commitments in the previous five years, when determining a most deserving applicant for the award of new work-bid exploration permits. Refer to **Appendix A** for a diagram outlining the process.

D. If a company and/or its directors has had two or more exploration permit cancellations or expiries in default in the previous five years and only entered into one GSA, the Joint Authority may consider the outstanding default (where no GSA was entered into) when determining a most deserving applicant for the award of new work-bid exploration permits.

E. If a defaulting titleholder chooses not to access a GSA or is deemed to be ineligible, the defaulting titleholder and parent company where applicable and all associated directors will be considered to be ‘not in good standing’ with the Joint Authority for a period of five years. This is effective from the day the notice of permit cancellation or expiry was published in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0).

F. A GSA may only be relevant if a titleholder intends to continue petroleum exploration activities in Commonwealth waters through participation in bidding for new permits.

G. Entering into a GSA will not delay any cancellation proceedings. Where companies have applied for a GSA prior to cancellation or expiry in default, the two processes can run in parallel.

H. Regardless of a cancellation, surrender or GSA application, as long as a title remains active the regulatory requirements for the title must be met - including the submission of Annual Titles Assessments Reports (ATARs) and payment of annual levies.

I. The Commonwealth, on behalf of all Joint Authorities, maintains a ‘National Standing Register’. This confidential register includes details of defaulting titleholders and whether a GSA was entered into or not, key dates relevant to the defaulting title and GSA, monetary value of the GSA, how the GSA will be discharged, and company directors.

J. The application form on NOPTA’s website and the [Regional Studies Factsheet](http://www.nopta.gov.au/factsheets/good-standing-agreement-regional-studies.html) provide further guidance on the information that should be submitted with a request for a GSA and the GSA process.

K. NOPTA’s role is to assess GSA requests to determine if the circumstances of the work program default meet the eligibility criteria and confirm the current market value of the default. NOPTA will provide advice to the Joint Authority to inform its decision.

L. Following acceptance of the GSA value, the Commonwealth member of the Joint Authority acts as an agent for the Joint Authority to finalise the GSA terms.

## Options for satisfying a Good Standing Agreement

* 1. *Qualifying permits*
     1. Qualifying permits are new exploration permits resulting from bidding within two acreage release rounds, as stipulated in the executed GSA.
     2. Bids must be uncontested – no other valid applications made for that release area.
     3. Only completed guaranteed primary term operational activities in qualifying permits will be credited against the GSA.
     4. If a bid is lodged as a joint venture, the joint venture partner subject to the GSA must demonstrate that it has expended the GSA amount in the primary term of the permit.
  2. *Regional studies*
     1. Regional studies are projects of broad relevance to the Australian petroleum industry and aligned with government priorities.
     2. Projects are agreed on a case-by-case basis with the Joint Authority.
     3. Projects may be onshore or offshore.
     4. Projects are usually completed within three years from the date of the execution of the GSA, or another timeframe as agreed by the Joint Authority.
     5. Data generated from a regional study will become ‘open file’ in a timeframe agreed with the Joint Authority.
     6. Projects acquiring new data would usually only be considered over acreage not currently being explored for oil and gas.
     7. Where data collected under a regional study may inform future exploration in an area, the Joint Authority may elect to pause release of acreage for bidding in that area until data is made open file and accessible for all bidders.
  3. An individual GSA can be satisfied by either qualifying permits, regional studies or a combination of both.

## Application process

* 1. Once a titleholder has determined it cannot meet a guaranteed work program commitment and would like to enter into a GSA, NOPTA should be notified in writing (refer to the application form on NOPTA’s website).
     + - Companies may apply in anticipation of a default and do not need to wait for a work program deadline to have passed.
  2. Any of the titleholders may choose not to apply for a GSA. However, if any of the titleholders do apply, all titleholders are to acknowledge and accept the eligibility criteria in sections 4.10 to 4.12. Those titleholders who are party to the executed GSA are only responsible for their participating equity share.
  3. A GSA request should be made on the application form on NOPTA’s website. Supporting information can be provided to outline:

1. The titleholder’s reasons for defaulting.
2. The titleholder’s costings in relation to the current market value (in Australian dollars) of the outstanding work program commitments.
3. Any other matter(s) the titleholder(s) wish the Joint Authority to take into consideration.
   1. NOPTA may request additional information and specify a timeframe that it must be provided. Failure to provide the information in the specified timeframe may result in the GSA request being refused.
   2. NOPTA will assess the request and determine if the circumstances of the work program default meet the eligibility criteria and confirm the current market value of the default.
   3. NOPTA will provide advice to the relevant Joint Authority for decision.

## Criteria and eligibility

* 1. To access a GSA, the Joint Authority must be satisfied of matters including if the titleholder has made a significant attempt to assess the petroleum potential of the permit area. This includes *all* of the following:

1. The completion of at least key seismic surveying commitment/s.
2. Submission to NOPTA of all documentary information, data and relevant title assessment reports, relating to the permit, in accordance with the RMA regulations or work program commitments.
3. Acknowledgement that all relevant seismic and well data will become ‘open file’ once the permit is cancelled or expires in default, in accordance with the RMA regulations.
4. Written agreement the titleholders will make a public announcement on the GSA within three months of its execution. It is the responsibility of the titleholders to provide a copy of the public announcement to NOPTA. Failure to do so may result in termination of the GSA.
   * + - *Publicly listed companies*: an ASX company announcement.
       - *Private companies or international entities*: notification in a major Australian newspaper and a media release on the company website, where applicable.
   1. When assessing eligibility the Joint Authority may also take into account:
5. If work in excess of the next ranked bidder has been completed.
6. Work undertaken in the previous term (if the title has been renewed).
7. The past performance of the titleholders, including the existence of and compliance with GSAs.
8. Other matters as considered relevant by the Joint Authority.
   1. In the instance a company and/or its directors have defaulted on a previous GSA, the Joint Authority may refuse access to a new GSA.

## Multiple titleholders

* 1. The titleholders may agree for one or more of the titleholders to transfer GSA obligations to another titleholder party to the defaulted permit. The Joint Authority and NOPTA will play no role in negotiations other than being notified of the agreed percentage of monetary obligations for each party.
  2. The agreed percentage will be used to divide the monetary value of the GSA among those subject to the GSA. This must total 100 per cent of the value of the monetary value.

## Monetary value and non-acceptable deductions

* 1. NOPTA will establish the current market value of the defaulted guaranteed work program commitments.
  2. The establishment of the monetary value will take into account the current market value of the outstanding guaranteed work proposed by the titleholder and any supporting information submitted by the titleholders.
  3. Expenditure on completed guaranteed work program activities before the default permit year cannot be used to discount the value of the GSA. However, the value of any above-commitment work, as varied into the title, may be used to discount the value.
  4. The monetary value of the GSA will be apportioned to each titleholder consistent with the agreed percentage holdings for each party to the GSA.
  5. For the purposes of determining monetary value, non-acceptable deductions include:
     + - permit administration costs
       - costs associated with regulatory approvals, including environmental plans
       - expenditure on activities not on the work program (originally or as varied in)
       - expenditure on activities undertaken outside the permit area.

## Minimum terms of a Good Standing Agreement

* 1. The Joint Authority determines the terms and conditions of a GSA on a case-by-case basis taking into account all relevant information provided.
  2. Should the Joint Authority agree to regional studies, the studies are to be completed within three years from the date of the execution of the GSA. All information is to be submitted to the Australian Government and will be made publically available.
  3. Where a GSA will be discharged, in whole or part, through qualifying permits, expenditure to be credited against the GSA must be expended on operational activities within the guaranteed primary term – refer to 4.1 of this guideline.
     + - Operational activities for the purposes of the GSA include acquisition, processing and interpretation of new geophysical and geochemical data and/or drilling activities.
       - Reprocessing of seismic data may be used if the original data was recorded after the date the qualifying permit was granted.
  4. In accordance with the eligibility criteria (refer to 4.10 of this guideline), those subject to the GSA are to make a public announcement within three months from the date of the GSA and submit a copy of the announcement to NOPTA.
  5. A GSA does not oblige bids on future acreage releases.
  6. If those subject to a GSA fail to fulfil the GSA commitments, the entity, the directors and where relevant the parent company will be considered to be ‘not in good standing’ with the Joint Authority for a period of five years effective from the day the notice of permit cancellation or expiry was published in the [Australian Government Gazette](https://www.legislation.gov.au/Browse/ByPublicationDate/Gazettes/InForce/0/0).

## Satisfaction of a Good Standing Agreement

* 1. Those subject to a GSA must notify NOPTA in writing and provide supporting evidence the GSA has been satisfied according to the terms of the GSA.
  2. Companies may be required to submit audited accounts demonstrating the required expenditure commitments have been met. Once this information has been received (and accepted) and all deliverables completed and all data delivered, titleholders will receive confirmation that the requirements of the GSA have been satisfied. The GSA record will be removed from the ‘National Standing Register’ and the past performance issue that led to the GSA will not be taken into account by the Joint Authority.
  3. A GSA will be satisfied by fulfilment of the agreement in respect of:
     1. *Qualifying permit/s:* the completion of the guaranteed primary work program/expenditure of the GSA amount. The guaranteed work program expenditure may include above commitment operational activities that have been formally varied into the work program. The onus is on the GSA-holder to confirm the above commitment work will satisfy the requirements of sections 2.18 to 2.27 of this guideline.
     2. *Regional studies:* the completion of the studies within the agreed timeframe (nominally three years from the date of the execution of the GSA) and the submission of all data and/or other deliverables to the Australian Government.
  4. For the purposes of satisfying a GSA, non-acceptable expenditure includes:
     + - permit administration costs
       - costs associated with regulatory approvals, including environmental plans
       - expenditure on activities not on the work program (originally or as varied in)
       - expenditure on regional studies not agreed in advance with the Joint Authority.

## Extensions

* 1. The Joint Authority may consider granting an extension to the timeframe in which a GSA must be satisfied, but only if the GSA-holder can demonstrate it has attempted to satisfy the GSA at every opportunity.
  2. An extension to the timeframe in which the GSA must be satisfied will be considered on a case-by-case basis.
  3. A written request to extend can be submitted to NOPTA for Joint Authority consideration and decision.

## Variation to Terms and Conditions

* 1. The Joint Authority may consider granting a variation of the terms and conditions of a GSA. This may include variation of the option to satisfy the GSA or to combine existing GSAs.
  2. Variations will be considered on a case-by-case basis.
  3. A written request to vary a GSA can be submitted to NOPTA for Joint Authority consideration and decision.
  4. If the request is to vary in the regional study option, the request should include an outline of the proposed regional study.

**[[1]](#footnote-2)**

APPENDICES

## Good Standing Agreement – Flow Chart

Default on guaranteed work program commitment occurs

Titleholder requests access to a GSA?

Eligibility?

*assessed by NOPTA*

Value assessment and GSA offer made by Joint Authority

Yes

No

Value accepted by titleholder

Value not accepted by titleholder

Commonwealth prepares GSA terms and documents for signing

GSA document signed by all parties

Title holder considered in good standing

GSA   
satisfied

GSA   
defaulted

The Joint Authority may use the defaulted guaranteed work program commitments and/or the defaulted GSA when using ‘past performance’ criteria

Yes, eligible.   
Notify titleholder

Not eligible   
Notify titleholder

Cancellation gazetted

Titleholder has chosen not to enter a GSA

1. Table of revisions

   | **Date** | **Version** | **Purpose** | **Jurisdiction** |
   | --- | --- | --- | --- |
   | February 2020 | 8 | Update the new department name | Cth |
   | July 2019 | 7 | Updated to reflect policy changes to acreage release and good standing agreements as well as process clarifications. | Cth |
   | May 2016 | 6 | Updated to reference prior usage right requirements under the *Environment Protection and Biodiversity Conservation Act 1999* | Cth |
   | May 2015 | 5 | Consolidating and streamlining of the Exploration Permit Guideline: *Requirements of Bid and Renewal Applications*, Exploration Permit Guideline: *Assessment of Bid and Renewal Applications* and the Exploration Permit Guideline: *Permit Conditions and Administration* into a single guideline. Wholesale re-write to improve clarity of Joint Authority expectations. Provision of additional flexibility through the primary term becoming a guaranteed three year block of time. Expanded options to satisfy a GSA. | Cth |
   | November 2011 | 4 | Updated to reflect changes to OPGGSA—transfer to NOPTA. Slight Amendments to the financial requirements (paragraph 5.1.2) | Cth |
   | November 2010 | 3 | Wholesale re-write to improve clarity of Joint Authority expectations | Cth |
   | October 2009 | 2 | Update to reflect:  * OPGGSA numbering * Grammatical errors | Cth |

   [↑](#footnote-ref-2)